## Milestone 12-10-2020
Milestone Reports
Milestone 1 - Analysis
[5 empty] | Deviation |  | % Deviation |  |  |  | Analysis Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | Virtual BTF | 7 | 43 |  | 36 |  | 514.3% |  | Red |  | Amber | 2
2 | CPG 2.0 drop 2 –sprint 2 | 10 | 16 |  | 6 |  | 60% |  | Amber |  | Green | 1
3 | Electronic Asset Movement Form (EMAF) | 10 | 22 |  | 12 |  | 120% |  | Red |  | Red | 2
4 | 9 Mobile Sim Swap CR - Phase 2 | 24 | 39 |  | 15 |  | 62.5% |  | Amber |  | Grand Total | 5
5 | Asset disposal form | 5 | 3 |  | -2 |  | -40% |  | Green | SDD to be completed on the 13th of Oct
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 56 | 123 | 0 | 67 |  | 119.6%
Milestone 2 - Development
[5 empty] | Deviation |  | % Deviation |  |  |  | Development Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | E-ballot CR | 60 | 14 |  | -46 |  | -76.67% |  | Green |  | Amber | 1
2 | YelloDoc CR – Sprint 2 | 21 | 32 |  | 11 |  | 52.38% |  | Amber |  | Green | 4
3 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - UI | 11 | 6 |  | -5 |  | -45.45% |  | Green |  | (blank) | 1
4 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - Integration |  |  |  | 0 |  | #DIV/0! |  |  | Development resource constraint to proceed | Grand Total | 6
5 | CSI portal | 55 | 35 |  | -20 |  | -36.36% |  | Green
6 | Online health Declaration | 45 | 20 |  | -25 |  | -55.56% |  | Green
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 192 | 107 | 0 | -85 |  | -44.27%
Milestone 3 - IAT
[5 empty] | Deviation |  | % Deviation |  |  |  | IAT Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | Share UI Revamp – Drop 2 (Div/Dept Pages) | 25 | 30 |  | 5 |  | 0.2 |  | Amber
2 |  |  |  |  | 0 |  | #DIV/0!
3 |  |  |  |  | 0 |  | #DIV/0!
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 25 | 30 | 0 | 5 |  | 0.2
Milestone 3 - SIT/UAT
[5 empty] | Deviation |  | % Deviation |  |  |  | SIT/UAT Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | CPG 2.0 drop 2 – Sprint 1 | 10 | 25 |  | 15 |  | 150% |  | Red |  | Amber | 1
2 | TSS CR – Medical Flow | 47 | 82 |  | 35 |  | 74.47% |  | Red |  | Green | 1
3 | Share UI Revamp – Drop 1 (Div/Dept Pages) | 28 | 28 |  | 0 |  | 0% |  | Green | Awaiting Deployment | Red | 1
4 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Grand Total | 3
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 85 | 135 | 0 | 50 |  | 58.82%
Milestone 4 - Sanity
[5 empty] | Deviation |  | % Deviation |  |  |  | Sanity Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | DM 360 (Reports Migration) | 10 | 81 |  | 71 |  | 710% |  | Red |  | Red | 3
2 | CPG 2.0 Phase 1 | 10 | 149 |  | 139 |  | 1390% |  | Red |  | Grand Total | 3
3 | E-Test | 8 | 20 |  | 12 |  | 150% |  | Red
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 28 | 250 | 0 | 222 |  | 792.9%

## Milestone 19-10-2020
[8 empty] | Red | % Deviation is more than 70%
| Milestone Reports | [6 empty] | Amber | % Deviation is above 0% to 69%
[8 empty] | Green | % Deviation is equal to and less than 0%
Milestone 1 - Analysis
[5 empty] | Deviation |  | % Deviation |  |  |  | Analysis Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | Virtual BTF | 7 | 48 |  | 41 |  | 585.7% |  | Red |  | Amber | 3
2 | CPG 2.0 drop 2 –sprint 2 | 10 | 21 |  | 11 |  | 110% |  | Red |  | Red | 2
3 | Electronic Asset Movement Form (EMAF) | 10 | 27 |  | 17 |  | 170% |  | Red | SDD pendig on MTNN | Grand Total | 5
4 | 9 Mobile Sim Swap CR - Phase 2 | 24 | 44 |  | 20 |  | 83.33% |  | Red
5 | Asset disposal form | 5 | 8 |  | 3 |  | 60% |  | Amber | SDD to be completed on the 13th of Oct
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 56 | 148 | 0 | 92 |  | 164.3% |  | Red
Milestone 2 - Development
[5 empty] | Deviation |  | % Deviation |  |  |  | Development Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | E-ballot CR | 60 | 19 |  | -41 |  | -68.33% |  | Green |  | Amber | 1
2 | YelloDoc CR – Sprint 2 | 21 | 37 |  | 16 |  | 76.19% |  | Red |  | Green | 4
3 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - UI | 11 | 11 |  | 0 |  | 0% |  | Green | Development of 20 UIs completed, pending Integration | (blank) | 1
4 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - Integration |  |  |  | 0 |  | #DIV/0! |  |  | Development resource constraint to proceed | Grand Total | 6
5 | CSI portal | 55 | 40 |  | -15 |  | -27.27% |  | Green
6 | Online health Declaration | 45 | 25 |  | -20 |  | -44.44% |  | Green
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 192 | 132 | 0 | -60 |  | -31.25% |  | Green
Milestone 3 - IAT
[5 empty] | Deviation |  | % Deviation |  |  |  | IAT Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | Share UI Revamp – Drop 2 (Div/Dept Pages) | 25 | 35 |  | 10 |  | 0.4 |  | Amber | Pending completion on one last department having access issues
2 |  |  |  |  | 0 |  | #DIV/0!
3 |  |  |  |  | 0 |  | #DIV/0!
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 25 | 35 | 0 | 10 |  | 0.4 |  | Amber
Milestone 3 - SIT/UAT
[5 empty] | Deviation |  | % Deviation |  |  |  | SIT/UAT Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | CPG 2.0 drop 2 – Sprint 1 | 10 | 30 |  | 20 |  | 200% |  | Red |  | Amber | 1
2 | TSS CR – Medical Flow | 47 | 87 |  | 40 |  | 85.11% |  | Red |  | Green | 1
3 | Share UI Revamp – Drop 1 (Div/Dept Pages) | 28 | 28 |  | 0 |  | 0% |  | Green | Awaiting Deployment | Red | 1
4 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Grand Total | 3
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 85 | 145 | 0 | 60 |  | 70.59% |  | Red
Milestone 4 - Sanity
[5 empty] | Deviation |  | % Deviation |  |  |  | Sanity Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | DM 360 (Reports Migration) | 10 | 86 |  | 76 |  | 760% |  | Red |  | Red | 3
2 | CPG 2.0 Phase 1 | 10 | 154 |  | 144 |  | 1440% |  | Red |  | Grand Total | 3
3 | E-Test | 8 | 25 |  | 17 |  | 212.5% |  | Red
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 28 | 265 | 0 | 237 |  | 846.4% |  | Red

## Milestone 26-10-2020
[8 empty] | Red | % Deviation is equal to and more than 70%
| Milestone Reports | [6 empty] | Amber | % Deviation is above 0% to 69%
[8 empty] | Green | % Deviation is less than and equal to 0%
Milestone 1 - Analysis
[5 empty] | Deviation |  | % Deviation |  |  |  | Analysis Stage
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | Virtual BTF | 7 | 53 |  | 46 |  | 657.1% |  | Red | Suspended | Row Labels | Count of Project
2 | CPG 2.0 drop 2 –sprint 2 | 10 | 26 |  | 16 |  | 160% |  | Red |  | Red | 5
3 | Electronic Asset Movement Form (EMAF) | 10 | 27 |  | 17 |  | 170% |  | Red | Requirement document has been approved | (blank)
4 | 9 Mobile Sim Swap CR - Phase 2 | 24 | 49 |  | 25 |  | 104.2% |  | Red |  | Grand Total | 5
5 | Asset disposal form | 5 | 13 |  | 8 |  | 160% |  | Red | SDD to be completed on the 13th of Oct
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 56 | 168 | 0 | 112 |  | 200% |  | Red
Milestone 2 - Development
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | E-ballot CR | 60 | 24 |  | -36 |  | -60% |  | Green |  | Green | 4
2 | YelloDoc CR – Sprint 2 | 21 | 42 |  | 21 |  | 100% |  | Red |  | Red | 1
3 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - UI | 11 | 11 |  | 0 |  | 0% |  | Green | Development of 20 UIs completed, pending Integration | (blank) | 1
4 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - Integration |  |  |  | 0 |  | #DIV/0! |  |  | Development resource constraint to proceed | Grand Total | 6
5 | CSI portal | 55 | 45 |  | -10 |  | -18.18% |  | Green
6 | Online health Declaration | 45 | 30 |  | -15 |  | -33.33% |  | Green
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 192 | 152 | 0 | -40 |  | -20.83% |  | Green
Milestone 3 - IAT
[5 empty] | Deviation |  | % Deviation |  |  |  | Row Labels | Count of Project
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Amber | 1
1 | Share UI Revamp – Drop 2 (Div/Dept Pages) | 25 | 36 |  | 11 |  | 0.44 |  | Amber | Completed Ready for Deployment | (blank)
2 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Grand Total | 1
3 |  |  |  |  | 0 |  | #DIV/0!
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 25 | 36 | 0 | 11 |  | 0.44 |  | Amber
Milestone 3 - SIT/UAT
[5 empty] | Deviation |  | % Deviation |  |  |  | Row Labels | Count of Project
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Green | 1
1 | CPG 2.0 drop 2 – Sprint 1 | 10 | 35 |  | 25 |  | 250% |  | Red |  | Red | 2
2 | TSS CR – Medical Flow | 47 | 92 |  | 45 |  | 95.74% |  | Red |  | (blank)
3 | Share UI Revamp – Drop 1 (Div/Dept Pages) | 28 | 28 |  | 0 |  | 0% |  | Green | Awaiting Deployment | Grand Total | 3
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 85 | 155 | 0 | 70 |  | 82.35% |  | Red
Milestone 4 - Sanity
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | DM 360 (Reports Migration) | 10 | 91 |  | 81 |  | 810% |  | Red |  | Red | 3
2 | CPG 2.0 Phase 1 | 10 | 159 |  | 149 |  | 1490% |  | Red |  | (blank)
3 | E-Test | 8 | 26 |  | 18 |  | 225% |  | Red | Completed | Grand Total | 3
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 28 | 276 | 0 | 248 |  | 885.7% |  | Red

## Milestone 02-11-2020
[8 empty] | Red | % Deviation is equal to and more than 30%
| Milestone Reports | [6 empty] | Amber | % Deviation is above 0% to 29%
[8 empty] | Green | % Deviation is less than and equal to 0% |  |  |  | Stage | Project | %Deviation
| Milestone 1 - Analysis | [11 empty] | Analysis | CPG 2.0 drop 2 –sprint 2 | 160% | Sum of %Deviation | Column Labels
[5 empty] | Deviation |  | % Deviation | [5 empty] | Analysis | Asset disposal form | 260% | Row Labels | Asset disposal form | CPG 2.0 drop 2 – Sprint 1 | CPG 2.0 drop 2 –sprint 2 | CPG 2.0 Phase 1 | CSI portal | DM 360 (Reports Migration) | E-ballot CR | E-Test | Online health Declaration | Share UI Revamp – Drop 1 (Div/Dept Pages) | Share UI Revamp – Drop 2 | Share UI Revamp – Drop 2 (Div/Dept Pages) | TSS CR – Medical Flow | YelloDoc CR – Sprint 2 | Grand Total
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment |  |  | Development | E-ballot CR | -51.67% | Analysis | 2.6 |  | 1.6 | [11 empty] | 4.2
1 | Virtual BTF | 7 | 53 |  | 46 |  | 657.1% |  | Red | Suspended |  |  | Development | YelloDoc CR – Sprint 2 | 123.8% | Development |  |  |  |  | -0.036364 |  | -0.51667 |  | -0.11111 |  | 0 |  |  | 1.2381 | 0.57395
2 | CPG 2.0 drop 2 –sprint 2 | 10 | 26 |  | 16 |  | 160% |  | Red |  | Row Labels | Count of Project | Development | Share UI Revamp – Drop 2 | 0% | IAT | [11 empty] | 0.44 |  |  | 0.44
3 | 9 Mobile Sim Swap CR - Phase 2 | 24 | 49 |  | 25 |  | 104.2% |  | Red | Suspended | Red | 4 | Development | CSI portal | -3.636% | Sanity |  |  |  | 15.5 |  | 8.6 |  | 2.25 | [6 empty] | 26.35
4 | Asset disposal form | 5 | 18 |  | 13 |  | 260% |  | Red | SDD to be completed on the 13th of Oct | (blank) |  | Development | Online health Declaration | -11.11% | SIT/UAT |  | 3 | [7 empty] | 0 |  |  | 1.0638 |  | 4.0638
5 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Grand Total | 4 | IAT | Share UI Revamp – Drop 2 (Div/Dept Pages) | 0.44 | Grand Total | 2.6 | 3 | 1.6 | 15.5 | -0.036364 | 8.6 | -0.51667 | 2.25 | -0.11111 | 0 | 0 | 0.44 | 1.0638 | 1.2381 | 35.6278
6 |  |  |  |  | 0 |  | #DIV/0! | [5 empty] | SIT/UAT | CPG 2.0 drop 2 – Sprint 1 | 300%
| Total | 46 | 146 | 0 | 100 |  | 217.4% |  | Red |  |  |  | SIT/UAT | TSS CR – Medical Flow | 106.4%
[13 empty] | SIT/UAT | Share UI Revamp – Drop 1 (Div/Dept Pages) | 0%
[13 empty] | Sanity | DM 360 (Reports Migration) | 860%
[8 empty] | Red | % Deviation is equal to and more than 11% |  |  |  | Sanity | CPG 2.0 Phase 1 | 1550%
[8 empty] | Amber | % Deviation is above 0% to 10% |  |  |  | Sanity | E-Test | 225%
[8 empty] | Green | % Deviation is less than and equal to 0%
Milestone 2 - Development
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | E-ballot CR | 60 | 29 |  | -31 |  | -51.67% |  | Green |  | Green | 4
2 | YelloDoc CR – Sprint 2 | 21 | 47 |  | 26 |  | 123.8% |  | Red | At Risk, as developer is still yet to release for IAT to commence 02/11/2020 | Red | 1
3 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - UI | 11 | 11 |  | 0 |  | 0% |  | Green | Development of 20 UIs completed, pending Integration | (blank) | 1
4 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - Integration |  |  |  | 0 |  | #DIV/0! |  |  | Development resource constraint to proceed | Grand Total | 6
5 | CSI portal | 55 | 53 |  | -2 |  | -3.636% |  | Green
6 | Online health Declaration | 45 | 40 |  | -5 |  | -11.11% |  | Green
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 192 | 180 | 0 | -12 |  | -6.25% |  | Green
Milestone 3 - IAT
[5 empty] | Deviation |  | % Deviation |  |  |  | Row Labels | Count of Project
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Amber | 1
1 | Share UI Revamp – Drop 2 (Div/Dept Pages) | 25 | 36 |  | 11 |  | 0.44 |  | Amber | Completed Ready for Deployment | (blank)
2 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Grand Total | 1
3 |  |  |  |  | 0 |  | #DIV/0!
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 25 | 36 | 0 | 11 |  | 0.44 |  | Amber
Milestone 3 - SIT/UAT
[5 empty] | Deviation |  | % Deviation |  |  |  | Row Labels | Count of Project
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Green | 1
1 | CPG 2.0 drop 2 – Sprint 1 | 10 | 40 |  | 30 |  | 300% |  | Red |  | Red | 2
2 | TSS CR – Medical Flow | 47 | 97 |  | 50 |  | 106.4% |  | Red | Exited UAT. Ready for Deployment | (blank)
3 | Share UI Revamp – Drop 1 (Div/Dept Pages) | 28 | 28 |  | 0 |  | 0% |  | Green | Completed Ready for Deployment | Grand Total | 3
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 85 | 165 | 0 | 80 |  | 94.12% |  | Red
Milestone 4 - Sanity
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Row Labels | Count of Project
1 | DM 360 (Reports Migration) | 10 | 96 |  | 86 |  | 860% |  | Red |  | Red | 3
2 | CPG 2.0 Phase 1 | 10 | 165 |  | 155 |  | 1550% |  | Red |  | (blank)
3 | E-Test | 8 | 26 |  | 18 |  | 225% |  | Red | Completed | Grand Total | 3
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 28 | 287 | 0 | 259 |  | 925% |  | Red

## Milestone 09-11-2020
[8 empty] | Red | % Deviation is equal to and more than 30%
| Milestone Reports | [6 empty] | Amber | % Deviation is above 0% to 29%
[8 empty] | Green | % Deviation is less than and equal to 0%
Milestone 1 - Analysis
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Stage | Project | %Deviation
1 | Virtual BTF | 7 | 53 |  | 46 |  | 657.1% |  | Red | Suspended | Analysis | CPG 2.0 drop 2 –sprint 2 | 210%
2 | CPG 2.0 drop 2 –sprint 2 | 10 | 31 |  | 21 |  | 210% |  | Red |  | Development | E-ballot CR | -43.33%
3 | 9 Mobile Sim Swap CR - Phase 2 | 24 | 49 |  | 25 |  | 104.2% |  | Red | Suspended | Development | YelloDoc CR – Sprint 2 | 147.6%
4 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Development | Share UI Revamp – Drop 2 | 0%
5 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Development | CSI portal | -3.636%
[11 empty] | Development | Online Health | 0%
[11 empty] | IAT | Share UI Revamp – Drop 2 | 0.44
| Total | 41 | 133 | 0 | 92 |  | 224.4% |  | Red |  | SIT/UAT | CPG 2.0 drop 2 – Sprint 1 | 350%
[11 empty] | SIT/UAT | TSS CR | 106.4%
[11 empty] | SIT/UAT | Share UI Revamp – Drop 1 | 0%
[8 empty] | Red | % Deviation is equal to and more than 11% |  | SIT/UAT | CSI portal | -40%
[8 empty] | Amber | % Deviation is above 0% to 10% |  | SIT/UAT | Online Health | -100%
[8 empty] | Green | % Deviation is less than and equal to 0% |  | Sanity | DM 360 | 910%
| Milestone 2 - Development | [9 empty] | Sanity | CPG 2.0 Phase 1 | 1600%
[5 empty] | Deviation |  | % Deviation |  |  |  | Sanity | E-Test | 225%
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | E-ballot CR | 60 | 34 |  | -26 |  | -43.33% |  | Green
2 | YelloDoc CR – Sprint 2 | 21 | 52 |  | 31 |  | 147.6% |  | Red | At Risk, as developer is still yet to release for IAT to commence. Concerns about email delivery issues on Sharepoint test environment causing futher delay since 05/11/2020
3 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - UI | 11 | 11 |  | 0 |  | 0% |  | Green | Development of 20 UIs completed, pending Integration
4 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - Integration |  |  |  | 0 |  | #DIV/0! |  |  | Development resource constraint to proceed
5 | CSI portal | 55 | 53 |  | -2 |  | -3.636% |  | Green | Lost 6 days as recourse was sick. The voting and voting report will be completed 10th Nov
6 | Online health Declaration | 45 | 45 |  | 0 |  | 0% |  | Green | Resources was charged, we lost 10 working days. Submitted 9th Nov
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 192 | 195 | 0 | 3 |  | 1.562% |  | Green
Milestone 3 - IAT
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | Share UI Revamp – Drop 2 (Div/Dept Pages) | 25 | 36 |  | 11 |  | 0.44 |  | Amber | Completed Ready for Deployment
2 |  |  |  |  | 0 |  | #DIV/0!
3 |  |  |  |  | 0 |  | #DIV/0!
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 25 | 36 | 0 | 11 |  | 0.44 |  | Amber
Milestone 3 - SIT/UAT
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | CPG 2.0 drop 2 – Sprint 1 | 10 | 45 |  | 35 |  | 350% |  | Red
2 | TSS CR – Medical Flow | 47 | 97 |  | 50 |  | 106.4% |  | Red | Exited UAT. Ready for Deployment
3 | Share UI Revamp – Drop 1 (Div/Dept Pages) | 28 | 28 |  | 0 |  | 0% |  | Green | Completed Ready for Deployment
4 | CSI Portal | 5 | 3 |  | -2 |  | -40% |  | Green | The initiation to review stage has been in UAT since 3rd of Nov
5 | Online health Declaration | 5 | 0 |  | -5 |  | -100% |  | Green
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 95 | 173 | 0 | 78 |  | 82.11% |  | Red
Milestone 4 - Sanity
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | DM 360 (Reports Migration) | 10 | 101 |  | 91 |  | 910% |  | Red
2 | CPG 2.0 Phase 1 | 10 | 170 |  | 160 |  | 1600% |  | Red
3 | E-Test | 8 | 26 |  | 18 |  | 225% |  | Red | Completed Data migration planning in progress
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 28 | 297 | 0 | 269 |  | 960.7% |  | Red

## Milestone 16-11-2020
[8 empty] | Red | % Deviation is equal to and more than 30%
| Milestone Reports | [6 empty] | Amber | % Deviation is above 0% to 29%
[8 empty] | Green | % Deviation is less than and equal to 0%
Milestone 1 - Analysis
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Stage | Project | %Deviation
1 | Virtual BTF | 7 | 53 |  | 46 |  | 657.1% |  | Red | Suspended | Analysis | CPG 2.0 drop 2 –sprint 2 | 260%
2 | CPG 2.0 drop 2 –sprint 2 | 10 | 36 |  | 26 |  | 260% |  | Red |  | Analysis | E-Test/ORC Integration | -50%
3 | 9 Mobile Sim Swap CR - Phase 2 | 24 | 49 |  | 25 |  | 104.2% |  | Red | Suspended | Development | E-ballot CR | -43.33%
4 | E-Test/ORC Integration | 20 | 10 |  | -10 |  | -50% |  | Green |  | Development | EAMF | -75%
5 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Development | CSI portal | -3.636%
[11 empty] | Development | Online Health | 0%
[11 empty] | Development | ADF | 0%
| Total | 61 | 148 | 0 | 87 |  | 142.6% |  | Red |  | IAT | YelloDoc CR – Sprint 2 | 33.33%
[11 empty] | Development | ADF
[11 empty] | SIT/UAT | CPG 2.0 drop 2 – Sprint 1 | 400%
[8 empty] | Red | % Deviation is equal to and more than 11% |  | SIT/UAT | CSI Portal
[8 empty] | Amber | % Deviation is above 0% to 10% |  | SIT/UAT | Online Health | -100%
[8 empty] | Green | % Deviation is less than and equal to 0% |  | Sanity | DM 360 | 960%
| Milestone 2 - Development | [9 empty] | Sanity | CPG 2.0 Phase 1 | 1650%
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | E-ballot CR | 60 | 34 |  | -26 |  | -43.33% |  | Green
4 | Electronic Asset Movement | 20 | 5 |  | -15 |  | -75% |  | Green | Development resource constraint to proceed
5 | CSI portal | 55 | 53 |  | -2 |  | -3.636% |  | Green | Lost 6 days as recourse was sick. The voting and voting report will be completed 10th Nov
6 | Online health Declaration | 45 | 45 |  | 0 |  | 0% |  | Green | Resources was charged, we lost 10 working days. Submitted 9th Nov
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 180 | 137 | 0 | -43 |  | -23.89% |  | Green
Milestone 3 - IAT
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | YelloDoc CR – Sprint 2 | 3 | 4 |  | 1 |  | 33.33% |  | Red
2 |  |  |  |  | 0 |  | #DIV/0!
3 |  |  |  |  | 0 |  | #DIV/0!
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 3 | 4 | 0 | 1 |  | 0.33333 |  | Amber
Milestone 3 - SIT/UAT
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | CPG 2.0 drop 2 – Sprint 1 | 10 | 50 |  | 40 |  | 400% |  | Red
4 | CSI Portal | 5 |  |  | -5 |  | -100% |  | Green | The initiation to review stage has been in UAT since 3rd of Nov
5 | Online health Declaration | 5 | 0 |  | -5 |  | -100% |  | Green
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 20 | 50 | 0 | 30 |  | 150% |  | Red
Milestone 4 - Sanity
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | DM 360 (Reports Migration) | 10 | 106 |  | 96 |  | 960% |  | Red
2 | CPG 2.0 Phase 1 | 10 | 175 |  | 165 |  | 1650% |  | Red
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 20 | 281 | 0 | 261 |  | 1305% |  | Red

## Milestone 23-11-2020
[8 empty] | Red | % Deviation is equal to and more than 30%
| Milestone Reports | [6 empty] | Amber | % Deviation is above 0% to 29%
[8 empty] | Green | % Deviation is less than and equal to 0%
Milestone 1 - Analysis
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Stage | Project | %Deviation
1 | Virtual BTF | 7 | 53 |  | 46 |  | 657.1% |  | Red | Suspended | Analysis | CPG 2.0 drop 2 –sprint 2 | 310%
2 | CPG 2.0 drop 2 –sprint 2 | 10 | 41 |  | 31 |  | 310% |  | Red |  | Analysis | E-Test/ORC Integration | -25%
3 | 9 Mobile Sim Swap CR - Phase 2 | 24 | 49 |  | 25 |  | 104.2% |  | Red | Suspended | Development | E-ballot CR | -35%
4 | E-Test/ORC Integration | 20 | 15 |  | -5 |  | -25% |  | Green |  | Development | EAMF | -50%
5 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Development | CSI portal | -3.636%
[11 empty] | Development | Online Health | 0%
[11 empty] | Development | ADF
| Total | 61 | 158 | 0 | 97 |  | 159% |  | Red |  | SIT/UAT | YelloDoc CR – Sprint 2
[11 empty] | SIT/UAT | CPG 2.0 drop 2 – Sprint 1 | 450%
[11 empty] | SIT/UAT | CSI Portal | 500%
[8 empty] | Red | % Deviation is equal to and more than 11% |  | SIT/UAT | Online Health | -50%
[8 empty] | Amber | % Deviation is above 0% to 10% |  | Sanity | DM 360 | 1010%
[8 empty] | Green | % Deviation is less than and equal to 0% |  | Sanity | CPG 2.0 Phase 1 | 1700%
| Milestone 2 - Development | [9 empty] | Sanity | E-Test | 225%
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | E-ballot CR | 60 | 39 |  | -21 |  | -35% |  | Green
4 | Electronic Asset Movement | 20 | 10 |  | -10 |  | -50% |  | Green | Development resource constraint to proceed
5 | CSI portal | 55 | 53 |  | -2 |  | -3.636% |  | Green | Lost 6 days as recourse was sick. The voting and voting report will be completed 10th Nov
6 | Online health Declaration | 45 | 45 |  | 0 |  | 0% |  | Green | Resources was charged, we lost 10 working days. Submitted 9th Nov
7 | ADF |  |  |  | 0 |  | #DIV/0!
| Total | 180 | 147 | 0 | -33 |  | -18.33% |  | Green
Milestone 3 - IAT
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 |  |  |  |  | 0 |  | #DIV/0!
2 |  |  |  |  | 0 |  | #DIV/0!
3 |  |  |  |  | 0 |  | #DIV/0!
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 0 | 0 | 0 | 0 |  | #DIV/0! |  | Amber
Milestone 3 - SIT/UAT
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | CPG 2.0 drop 2 – Sprint 1 | 10 | 55 |  | 45 |  | 450% |  | Red
4 | CSI Portal | 2 | 12 |  | 10 |  | 500% |  |  | The initiation to review stage has been in UAT since 3rd of Nov
5 | Online health Declaration (IAT) | 3 | 2 |  | -1 |  | -33.33% |  | Green
6 | YelloDoc CR – Sprint 2 | 5 |  |  | -5 |  | -100% |  | Green
7 | Online health Declaration (UAT) | 4 | 2 |  | -2 |  | -50% |  | Green
8 |  |  |  |  | 0 |  | #DIV/0!
9 |  |  |  |  | 0 |  | #DIV/0!
10 |  |  |  |  | 0 |  | #DIV/0!
| Total | 24 | 71 | 0 | 47 |  | 195.8% |  | Red
Milestone 4 - Sanity
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | DM 360 (Reports Migration) | 10 | 111 |  | 101 |  | 1010% |  | Red
2 | CPG 2.0 Phase 1 | 10 | 180 |  | 170 |  | 1700% |  | Red
4 | E-Test | 8 | 26 |  | 18 |  | 225% |  | Red | Completed. Data Migration Planning in progress
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 28 | 317 | 0 | 289 |  | 1032% |  | Red

## Milestone 30-11-2020
[8 empty] | Red | % Deviation is equal to and more than 30%
| Milestone Reports | [6 empty] | Amber | % Deviation is above 0% to 29%
[8 empty] | Green | % Deviation is less than and equal to 0%
Milestone 1 - Analysis
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment | Stage | Project | %Deviation
1 | Virtual BTF | 7 | 53 |  | 46 |  | 657.1% |  | Red | Suspended | Analysis | CPG 2.0 drop 2 –sprint 2 | 350%
2 | CPG 2.0 drop 2 –sprint 2 | 10 | 45 |  | 35 |  | 350% |  | Red |  | Analysis | E-Test/ORC Integration | 0%
3 | 9 Mobile Sim Swap CR - Phase 2 | 24 | 49 |  | 25 |  | 104.2% |  | Red | Suspended | Development | E-ballot CR | -26.67%
4 | E-Test/ORC Integration | 20 | 20 |  | 0 |  | 0% |  | Green | Awaiting development resource identification | Development | EAMF | -25%
5 |  |  |  |  | 0 |  | #DIV/0! |  |  |  | Development | ADF | 0%
[11 empty] | Development | Online Health | 0%
[11 empty] | Development | ADF
| Total | 61 | 167 | 0 | 106 |  | 173.8% |  | Red |  | SIT/UAT | Online Health | -50%
[11 empty] | Sanity | DM 360 | 1010%
[11 empty] | Sanity | CPG 2.0 Phase 1 | 1700%
[8 empty] | Red | % Deviation is equal to and more than 11% |  | Sanity | E-Test | 225%
[8 empty] | Amber | % Deviation is above 0% to 10% |  | Sanity | CPG 2.0 Drop 2-Sprint 1 | -50%
[8 empty] | Green | % Deviation is less than and equal to 0%
Milestone 2 - Development
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | E-ballot CR | 60 | 44 |  | -16 |  | -26.67% |  | Green
2 | Electronic Asset Movement | 20 | 15 |  | -5 |  | -25% |  | Green | Development resource constraint to proceed
3 | ADF (AS-IS) | 5 | 5 |  | 0 |  | 0% |  | Green | Lost 6 days as recourse was sick. The voting and voting report will be completed 10th Nov
4 | ADF | 10 | 10 |  | 0 |  | 0% |  | Green | Resources was charged, we lost 10 working days. Submitted 9th Nov
5 | Share UI Revamp – Drop 2 (Custom WFs/Apps) - Integration |  | 20 | [6 empty] | Development resource constraint to proceed
7
| Total | 95 | 94 | 0 | -1 |  | -1.053% |  | Green
Milestone 3 - IAT
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 |  |  |  |  | 0 |  | #DIV/0!
2 |  |  |  |  | 0 |  | #DIV/0!
3 |  |  |  |  | 0 |  | #DIV/0!
4 |  |  |  |  | 0 |  | #DIV/0!
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 0 | 0 | 0 | 0 |  | #DIV/0! |  | Amber
Milestone 3 - SIT/UAT
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | Online health Declaration (UAT) | 4 | 2 |  | -2 |  | -50% |  | Green | Closed at 85%
2 |  |  |  |  | 0 |  | #DIV/0!
3 |  |  |  |  | 0 |  | #DIV/0!
4 |  |  |  |  | 0 |  | #DIV/0!
| Total | 4 | 2 | 0 | -2 |  | -50% |  | Red
Milestone 4 - Sanity
[5 empty] | Deviation |  | % Deviation
S/N | Project | Planned Duration | Duration to Date | Actual Duration | To Date | Actual | To Date | Actual | RAG Status | Comment
1 | DM 360 (Reports Migration) | 10 | 111 |  | 101 |  | 1010% |  | Red
2 | CPG 2.0 Phase 1 | 10 | 180 |  | 170 |  | 1700% |  | Red
3 | CPG 2.0 Drop 2-Sprint 1 | 10 | 5 |  | -5 |  | -50% |  | Green
4 | E-Test | 8 | 26 |  | 18 |  | 225% |  | Red | Completed. Data Migration Planning in progress
5 |  |  |  |  | 0 |  | #DIV/0!
6 |  |  |  |  | 0 |  | #DIV/0!
7 |  |  |  |  | 0 |  | #DIV/0!
| Total | 38 | 322 | 0 | 284 |  | 747.4% |  | Red